## RetailCo Project Plan DRAFT
RetailCo: Project Plan
Increasing the percentage of MWBE suppliers
Deploying $25M investment in MWBEs via. CDFI
|  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10
Sub-project | Phase | Activity | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
MWBE Supplier % | Research | Overall
MWBE Supplier % | Research | Identify stakeholders to interview (RetailCo procurement & external MWBE owners)
MWBE Supplier % | Research | Schedule and conduct interviews
MWBE Supplier % | Research | Develop quantitative survey and work with third party survey panel provider to deploy survey
MWBE Supplier % | Research | Manage survey panel provider to ensure quality and quantity of responses
MWBE Supplier % | Research | Consolidate insights from stakeholder interviews and quantitative survey to present to partner team and RetailCo leadership
MWBE Supplier % | Fact-base | Overall
MWBE Supplier % | Fact-base | Develop procurement data request / requirements to send to RetailCo
MWBE Supplier % | Fact-base | Develop shell deck to frame how to tell the story
MWBE Supplier % | Fact-base | Create data model to analyzeRetailCo inputs
MWBE Supplier % | Fact-base | Run data through model and analyze by all necessary criteria
MWBE Supplier % | Fact-base | Check with Finance and procurement counterparts to ensure accuracy before presenting to leaders
MWBE Supplier % | Fact-base | Consolidate factbase to present to partner team and RetailCo leadership
MWBE Supplier % | Strategy Dev. | Overall
MWBE Supplier % | Strategy Dev. | Create strategic hypothesis to test with client
MWBE Supplier % | Strategy Dev. | Prepare materials for client strategy worksession
MWBE Supplier % | Strategy Dev. | Hold strategy session with client leadership to co-create (vision, mission, strategic pillars, etc.)
MWBE Supplier % | Strategy Dev. | Refine strategy based on strategy session
MWBE Supplier % | Strategy Dev. | Share updated Strategy with client leadership
MWBE Supplier % | Roll out | Overall
MWBE Supplier % | Roll out | Identify quick-win opportunities to get ball rolling and use as success stories
MWBE Supplier % | Roll out | Train procurement staff to execute opportunities and to source additional in line with strategy
MWBE Supplier % | Roll out | Iterate on approach based on early learnings from quick win opportunities
MWBE Investment | Research | Overall
MWBE Investment | Research | Identify stakeholders to interview (RetailCo finance professionals, industry peers, etc.)
MWBE Investment | Research | Schedule and conduct interviews
MWBE Investment | Research | Consolidate interview insights to inform approach, including return requirements (financial & non)
MWBE Investment | Invest. Thesis | Overall
MWBE Investment | Invest. Thesis | Determine shell investment thesis and receive leadership approval re: content/format
MWBE Investment | Invest. Thesis | Develop investment thesis per approved structure (further planning to come)
MWBE Investment | Invest. Thesis | Share investment thesis with client for approval
MWBE Investment | Fund Options | Overall
MWBE Investment | Fund Options | Develop long-list of CDFI options, along with alternate investment management sources
MWBE Investment | Fund Options | Review each of the long-list fund options against all criteria from investment thesis
MWBE Investment | Fund Options | Develop initial short-list of potential fund options
MWBE Investment | Fund Options | Consolidate insights and short-list into update for leadership teams (BCG & RetailCo)
MWBE Investment | Op. Model | Overall
MWBE Investment | Op. Model | Determine relevant RetailCo stakeholders to oversee investment & play other roles as required
MWBE Investment | Op. Model | Clearly define roles, responsibilities, and decision rights for each stakeholder
MWBE Investment | Op. Model | Onboard stakeholders to the project and ensure they are prepared to interact with fund per R&R
MWBE Investment | Op. Model | Share Operating Model update with leadership teams
MWBE Investment | Short-list | Overall
MWBE Investment | Short-list | Conduct due diligence on each short-listed fund
MWBE Investment | Short-list | Priorize short-listed funds based on investment thesis
MWBE Investment | Selection | Overall
MWBE Investment | Selection | Develop recommendation materials with top options for approval from client
MWBE Investment | Selection | Present options to client for decision/approval